## Primary
Project Charter
Sheet 1 | Business Case | Details of the Client, viz., Industry sector-API/VET/Agro etc
Projection of overall requirement
Target price, if disclosable
Timelines available
ROS / Selected Route
Sheet 2 | Team | Details of Project team - TL / Chemist / ARD / Purchase / Support
Kick of meeting
Sheet 3 | Gantt Chart of Project | RM Procurement
Analytical requirements - Columns / Reagents procurement
Feasibility / Familiarization
Analytical support
Optimization
Sheet 4 | Meetings | Action points

## Business Case
Business Case
1 | Name of the Product | Ezetimibe
2 | CAS No | 163222-33-1
3 | Project Code | EZM
4 | Client Name
5 | Servicable / Applicable Industry
6 | Projected Quantity(in tonnage on annual basis)
7 | Target Price
8 | Timeline Availabe
9 | No of Routes Available
10 | Patent Available - Y/N
11 | Patent to be Filed - Y/N
12 | Final Selected Route
13 | Timeline for the Selected Route

## Team
Team
| Name of the Project Lead | Jadhav Balasaheb
| Name of the Chemist 1 | Swapnil Mahale
| Name of the Chemist 2 | Mahesh
| Name of the Chemist 3 | Ganesh wagh
| Name of the ARD Lead | Suresh J
| Name of the Executive | Guruprasad
| Name of the Analyst 1 [HPLC & GC] | Jagadeesh
| Name of the Analyst 2 [HPLC] | Shivanya
| Name of the Analyst 3 [WET Analysis] | Dhanesh
| SCM | Pradeep / Uday Bhaskar
| Stores | Satish
| DQA | Leela Mohan
| Engineer & Maintenance | Premchand
Process Engineer
| Project Management | Bhavani

## Task List for Gantt
Task List for Gantt Chart
S.No | Task | Dept Responsible | CRD point | Status as 22-03-2024 | Status as 30-03-2024 | Status as 06-04-2024 | Status as 12-04-2024 | Status as 16-04-2024 | Status as 26-04-2024 | Status as 27-04-2024 | No.of Working Days
[11 empty] | 11 | 12 | 13 | 14 | 15 | 16 | 18 | 19 | 20 | 21 | 22 | 23 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 8 | 10 | 11 | 12 | 13 | 15 | 16 | 18 | 19 | 20 | 22 | 23 | 24 | 25 | 26 | 27 | 29 | 30 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 18 | 20 | 21 | 22 | 23 | 24 | 25 | 27 | 28 | 29 | 30 | 31 | 1 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 15 | 17 | 18 | 19 | 20 | 21 | 22 | 24 | 25 | 26 | 27 | 28 | 29
1 | Product Specifications | DQA |  | USP specifications 30-03-2024 | Preparation to be completed today. [02-04-2024] | Not completed Date revised 10-04-2024 | Not completed on 10-04-2024 due to lack of communication between CRD ,ARD & DQA It will complete on 18-04-2024 | Not completed on 10-04-2024 due to lack of communication between CRD ,ARD & DQA It will complete on 18-04-2024 | Completed | bar: No.of Working Days 30
2 | Literature survey | CRD |  | Completed | Completed | Completed | Completed | Completed | Completed
3 | Selection of Route | CRD | completed | Completed | Completed | Completed | Completed | Completed | Completed
4 | Costing | CRD | after optimization
5 | Literature search - ARD | ARD |  | 2024-03-30 | Completed | Completed | Completed | Completed | Completed | bar: No.of Working Days 30
6 | RM Procurement for Lab work | SCM |  | Completed | Completed | Completed | Completed | Completed | Completed
7 | Analytical requirements - Columns / Reagents procurement | ARD/SCM |  | To be ordered [26-03-2024] | Initiated to SCM | 06-04-2024 [Sent for Approval] [18-05-2024] | EOD WILL BE Update by Pradeep | 06-04-2024 [Sent for Approval] [18-05-2024] | ARD: 1 chiral column and impurities are pending | Chiral column will receive on 04-05-2024 Impurities under procurement [SCM]
8 | Familiarization | CRD/ARD | [6 empty] | Completed
| Stage-01(Time = 45-50hr) | CRD | one batch completed,characteriaztion pending | 25-03-2024 to 29-03-2024 | Completed | Completed | Completed | Completed | bar: No.of Working Days 25 to No.of Working Days 29
| Stage-02 (Time = 75-80hr) | CRD | Not completed | 30-03-2024 to 06-04-2024 | Completed | Completed | Completed | Completed | Completed | bar: No.of Working Days 30 to No.of Working Days 6
| Stage-03(Time = 52hr) | CRD | Not completed | 10-04-2024 to 15-04-2024 | Completed | Completed | Completed | Completed | Completed | bar: No.of Working Days 10 to No.of Working Days 15
| Stage-04 (Time = 36hr) | CRD | Not completed | 16-04-2024 to 22-04-2024 | Completed | Completed | Completed | Completed | Completed | bar: No.of Working Days 16 to No.of Working Days 22
9 | Preparation or Procurement of IM and API standards | CRD/ARD/SCM
| IMT-1 Preparation | CRD |  | Completed | Completed | Completed | Completed | Completed | Completed
| IMT-2 Preparation | CRD |  | Completed | Completed | Completed | Completed | Completed | Completed
| API Standards | CRD |  | Completed | Completed | Completed | Completed | Completed | Completed
| IMT-1,IMT-2 & API Chraterisation Report | ARD |  | 2024-04-05 | 2024-04-05 | IMT-1 [11-04-2024] IMT-2 [12-04-2024] API [to be discussed with sir [06-04-2024]-Procure from outside | IMT-1 [completed] IMT-2 [12-04-2024]-Not completed Due to SOR Test is fail-once passing sample to be received from CRD Timelines will give on 16-04-2024 API-It will prepared in CRD [Sapthagiri sample] 25-04-2024 | IMT-2 [12-04-2024]-Not completed Due to SOR Test is fail-once passing sample to be received from CRD Timelines will give on 16-04-2024 It will complete on 19-04-2024 | Completed [IMT-1 & IMT-2 (20-04-2024)] CRD-SAMPLE SUBMITTED TO ARD API will complete on 25-04-2024 ARD: Based on revised characterization report format analysis is completed today it will be completed. 1 Day delay due to IR Report received today | Waiting for C,H,& N analysis reports It will complete on 03-05-2024 | bar: No.of Working Days 5
10 | Tentative analytical method development and report for IP, IM & API | ARD |  | 2024-04-02 | 2024-04-02 | Not Required | Not Required | Not Required | Not Required | bar: No.of Working Days 2
11 | Analytical support For Familiarization | ARD |  | 25-03-2024 to 22-04-2024 | 25-03-2024 to 22-04-2024 | 25-03-2024 to 22-04-2024 | bar: No.of Working Days 25 to No.of Working Days 22
12 | Familiarization Report | CRD
| Stage-01 |  |  | 30-03-2024 to 03-04-2024 | On time | 12-04-2024 [CRD & DQA] | Not completed on 12-04-2024 CRD Submitted 11-04-2024 [Stage-01,02 & 03] DQA will complete on 18-04-2024 | Completed [15-04-2024] | Completed [15-04-2024]
| Stage-02 |  |  | 10-04-2024 to 13-04-2024 |  |  |  | 2024-04-18 | Completed [18-04-2024] | bar: No.of Working Days 30 to No.of Working Days 3
| Stage-03 |  |  | 16-04-2024 to 19-04-2024 |  |  |  | 2024-04-18 | Completed [18-04-2024] | bar: No.of Working Days 10 to No.of Working Days 13
| Stage-04 |  |  | 23-04-2024 to 26-04-2024 |  |  | Not submitted CRD to DQA Due to Network issue on 11-04-2024 it will close on 16-04-2024 [CRD] DQA WILL COMPLETE ON 19-04-2024 | 2024-04-19 | CRD: CRD submitted on 15.04.24 to DQA under review DQA: it will completed on 26-04-2024 Due to lack of Manpower | DQA: Not completed It will complete on 30-04-2024 | bar: No.of Working Days 16 to No.of Working Days 19
13 | Forced Degradation followed by Identification and Procurement of Impurities and Report | ARD |  | Hold | bar: No.of Working Days 23 to No.of Working Days 26
14 | Optimization | CRD |  | Not Required | Not Required | Not Required | Not Required | Not Required | Not Required
Stage-01
Stage-02
Stage-03
Stage-04
15 | Analytical support | ARD
16 | Analytical Method Development | ARD
17 | Optimization Report
| Stage-01 | CRD
| Stage-02 | CRD
| Stage-03 | CRD
| Stage-04 | CRD
18 | Vendor Qualification | DQA |  | 2024-03-30 | bar: No.of Working Days 30
19 | Analytical Method Development Report | ARD |  | Not Required | Not Required | Not Required | Not Required | Not Required | Not Required
20 | Process Safety Studies - Hazop Studies & Risk Assessment [MSDS] | DQA |  | 2024-03-30 | 2024-04-06 | Completed [04-04-2024] | Completed | Completed | Completed | bar: No.of Working Days 30
21 | Demonstration of Process to the Engineers | CRD/TTR |  | Not Required | Not Required | Not Required | Not Required | Not Required | Not Required
| Stage-01 | CRD
| Stage-02 | CRD
| Stage-03 | CRD
| Stage-04 | CRD
22 | Tentative specifications of RM [12] | ARD |  |  | 06-04-2024 Except Titanium tetrachloride | Not completed it will complete on 12-04-2024 | SpecificationS [11] gave to CRD it will signoff 12-04-2024 [CRD & DQA] Titanium tetrachloride-Pradeep will update on Monday | SpecificationS [11] gave to CRD it will signoff 12-04-2024 [CRD & DQA] Titanium tetrachloride-Pradeep will update on Monday | Hydrogen peroxide & Titanium tetrachloride Specifications will complete on 26.04.24. Titanium tetrachloride MOA will get based on commercial PO as confirmed by Pradeep | H2O2: IT WILL COMPLETE ON 29-04-2024 TiCl4: IT WILL COMPLETE ON 29-04-2024
| Tentative STP RM [12] |  |  |  | To be finalised by Monday [DQA/SCM] |  | It will complete on 27-04-2024 [ARD] | It will complete on 27-04-2024 [ARD] |  | H2O2: It will complete on 29-04-2024 TiCl4: It will complete on after recived the MOA from DQA
Tentative specifications of IP, IM
| Stage-01 [IP & IM] |  |  |  | 2024-04-02 | Completed | Completed | Completed | Completed
| Stage-02 [IP & IM] |  |  |  | 2024-04-10 | 2024-04-10 | Completed | Completed | Completed
| Stage-03 [IP & IM] |  |  |  | 2024-04-17 | 2024-04-17 | Date revised due to 17-04-204 is holiday It will complete on 18-04-2024 | Date revised due to 17-04-204 is holiday It will complete on 18-04-2024 | Completed
Tentative STP's of IP, IM & API
| Stage-01 [IP & IM] |  |  |  | 2024-04-22 | 2024-04-22 | 2024-04-22 | 2024-04-22
Stage-02 [IP & IM]
Stage-03 [IP & IM]
| Stage-04 [IP & API] | [7 empty] | ARD: API STP not completed due to lack clarity on the test which we need to incorporate in the Spec | 26-04-2024-Cleared It will complete on 03-05-2024
23 | Equipment cleaning procedure | CRD |  |  |  | Completed | Completed | Completed | Completed
| Stage-01 |  |  |  | 2024-04-03 | bar: No.of Working Days 22 to No.of Working Days 23
| Stage-02 |  |  |  | 2024-04-10 | bar: No.of Working Days 15 to No.of Working Days 16
| Stage-03 |  |  |  | 2024-04-17 | bar: No.of Working Days 29 to No.of Working Days 30
Stage-04 | bar: No.of Working Days 7 to No.of Working Days 10
24 | Equipment cleaning analytical method [Based on UV Method] | ARD |  |  | 2024-04-17
25 | Process Write-up | CRD
| Stage-01 |  |  |  | 2024-04-01 | Completed | Completed | Completed | Completed | bar: No.of Working Days 20 to No.of Working Days 23
| Stage-02 |  |  |  | 2024-04-05 | Today will sign off | Completed [06-04-2024] | Completed [06-04-2024] | Completed [06-04-2024] | bar: No.of Working Days 14 to No.of Working Days 16
| Stage-03 |  |  |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | Not completed due to lack of man power It will complete on 16-04-2024 | Completed | bar: No.of Working Days 28 to No.of Working Days 30
| Stage-04 |  |  |  | 2024-04-20 | 2024-04-20 | 2024-04-20 |  | CRD: CRD submitted on 18.04.24 to DQA under review. DQA: It will complete on 29-04-2024 Due to lack of manpower | Date revised on 30-04-2024 Due to License documents work | bar: No.of Working Days 6 to No.of Working Days 10
26 | BPR preparation | DQA
| Stage-01 |  |  |  | 2024-04-02 | Completed |  |  | Completed [02-04-2024]
| Stage-02 |  |  |  | 2024-04-08 | 2024-04-08 | Completed [08-04-2024] | Completed [08-04-2024] | Completed [08-04-2024]
| Stage-03 |  |  |  | 2024-04-18 | 2024-04-18 | On time |  | it will complete 20-04-2024 Completed [24-04-2024]
| Stage-04 |  |  |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | It will complete on 29-04-2024 | Date revised on 30-04-2024 Due to License documents work
27 | Lab Validation | CRD | bar: No.of Working Days 17 to No.of Working Days 1
| Stage-01 |  | 14 days including analysis |  | 03-04-2024 to 08-04-2024 | completed [06-04-2024] | Completed | Completed | bar: No.of Working Days 3 to No.of Working Days 24
| Stage-02 |  | 18 days including analysis |  | 10-04-2024 to 18-04-2024 | 10-04-2024 to 18-04-2024 | In progress | bar: No.of Working Days 25 to No.of Working Days 29
| Stage-03 |  | 15 days including analysis |  | 19-04-2024 to 25-04-2024 | 19-04-2024 to 25-04-2024 |  |  | On time | COMPLETED
| Stage-04 |  | 16 days including analysis |  | 26-04-2024 to 30-04-2024 | 26-04-2024 to 30-04-2024 |  |  | This has to be started after the chiral purity of API obtained from familarisation is Known. | HOLD
28 | Analytical Support for Lab Validation | ARD |  |  |  | One week after Receiving the Columns | One week after Receiving the Columns
29 | Analytical Method Verification & Report | ARD |  |  |  |  | To be confirm with plant [16-04-2024] | Waiting for the Plant confirmation |  | Waiting for the Plant confirmation
30 | Analytical Method Transfer | ARD
31 | Preparation of PDR (as per format provided by DQA) | CRD | simultaneously with Lab validation
| Stage-01 |  |  |  | 11-04-2024 to 15-04-2024 | 11-04-2024 to 15-04-2024 | CRD Submitted to DQA ON 11-04-2024 |  | completed
| Stage-02 |  |  |  | 19-04-2024 to 22-04-2024 | 19-04-2024 to 22-04-2024 | 19-04-2024 to 22-04-2024 | 19-04-2024 to 22-04-2024 | CRD submitted 19.04.24 to DQA under review | COMPLETED
| Stage-03 |  |  |  | 16-04-2024 to 27-04-2024 | 16-04-2024 to 27-04-2024 | 16-04-2024 to 27-04-2024 | 16-04-2024 to 27-04-2024 | ontime | CRD WILL SUBMITT THE PDR REPORT TO DQA It will complete on 30-04-2024
| Stage-04 |  |  |  | 02-05-2024 to 08-05-2024 | 02-05-2024 to 08-05-2024 | 02-05-2024 to 08-05-2024 | 02-05-2024 to 08-05-2024
32 | PDR review and approval by DQA | DQA
| Stage-01 |  |  |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | Completed [16-04-2024]
| Stage-02 |  |  |  | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-23 | On time Completed [25-04-2024] | COMPLETED
| Stage-03 |  |  |  | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-04-29 |  | 2024-04-30
| Stage-04 |  |  |  | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2024-05-13
33 | Identification of Equipment for Scale-up | CRD/TTR
34 | Technology Transfer report by Engineers | CRD/TTR
35 | RM Procurement for Pilot batch | SCM
36 | Execution of Pilot batch | CRD/TTR
37 | Report on Pilot batch | TTR
38 | RM Procurement for Trail batch | SCM
39 | Execution of Trail batch | CRD/TTR/PD/QA
40 | Report on Trail batch | CRD/TTR/PD/QA
41 | Process Validation | PD/QC/TSD/QA
42 | Process Validation report | PD/QC/TSD/QA
43 | Finalization of all specifications and STPs | QC/QA
44 | Stability Study | QC/QA
45 | DMF Filing | QA/DQA

## RM LIST
Sr.no. | Name of the Material | Cas no. | Category
1 | 4-(4-fluoro benzoyl) butyric acid | 149437-76-3 | KSM-001
2 | S (+)-4-phenyl-2-Oxazolidinone | 99395-88-7 | KSM-002
3 | 4-(4-Hydroxybenzoylidene) fluoro aniline or | 3382-63-6 | KSM-003
4- [ [(4-Fluoro phenyl) imino] methyl] phenol
4 | (R)-(+)-2-Methyl-CBS-oxazaborolidine | 112022-83-0 | Reagent
5 | Borane dimethyl sulphide complex (10 M solution) | 13292-87-0 | Reagent
6 | Trimethyl silyl chloride | 75-77-4 | Reagent
7 | Titanium tetra chloride | 7550-45-0 | Reagent
8 | 4-Dimethyl amino pyridine (DMAP) | 1122-58-3 | Reagent
9 | N, O-Bis(trimethylsilyl)acetamide (BSA) | 10416-59-8 | Reagent
10 | Tetra-n-butyl ammonium fluoride trihydrate (TBAF) | 87749-50-6 | Reagent
11 | 30% Hydrogen peroxide | 7722-84-1 | Reagent
12 | Pivaloyl chloride | 3282-30-2 | Reagent
13 | Sodium sulfite (Na2SO3) | 7757-83-7 | Reagent
14 | Sodium metabisulphite (Na2S2O5) | 7681-57-4 | Reagent
15 | L (+) tartaric acid | 87-69-4 | Reagent
16 | Triethyl amine | 121-44-8 | Base
17 | Sodium bicarbontae | 144-55-8 | Base
18 | Potassium hydroxide | 1310-58-3 | Base
19 | Sulphuric acid | 7664-93-9 | Acid
20 | Acetic acid | 64-19-7 | Acid
21 | MDC | 79-09-2 | Solvent
22 | DMF | 68-12-2 | Solvent
23 | IPA | 67-63-0 | Solvent
24 | Methanol | 67-56-1 | Solvent
25 | Ethyl acetate | 141-78-6 | Solvent
26 | n-Heptane | 142-82-5 | Solvent
27 | Acetone | 67-64-1 | Solvent
28 | Sodium chloride | 7647-14-5 | --
29 | Activated charcoal | 7440-44-0 | --
30 | Hyflow supercel | 68855-54-9 | --