## Primary
Project Charter
Sheet 1 | Business Case | Details of the Client, viz., Industry sector-API/VET/Agro etc
Projection of overall requirement
Target price, if disclosable
Timelines available
ROS / Selected Route
Sheet 2 | Team | Details of Project team - TL / Chemist / ARD / Purchase / Support
Kick of meeting
Sheet 3 | Gantt Chart of Project | RM Procurement
Analytical requirements - Columns / Reagents procurement
Feasibility / Familiarization
Analytical support
Optimization
Sheet 4 | Meetings | Action points

## Business Case
Business Case
1 | Name of the Product | Fosravuconazole
2 | CAS No | 351227-64-0
3 | Project Code | FRZ
4 | Client Name
5 | Servicable / Applicable Industry
6 | Projected Quantity(in tonnage on annual basis)
7 | Target Price
8 | Timeline Availabe
9 | No of Routes Available
10 | Patent Available - Y/N
11 | Patent to be Filed - Y/N
12 | Final Selected Route
13 | Timeline for the Selected Route

## Team
Team
Name of the Project Lead
Name of the Chemist 1
Name of the Chemist 2
Name of the Chemist 3
Name of the ARD Lead
Name of the Executive
SCM
Stores
DQA
Engineer & Maintenance
Process Engineer
Project Management

## Planning
Task List for Gantt Chart
S.No | Task | 2026-06-06
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Product Specifications | 4 Weeks
2 | Literature survey | Complete
3 | Selection of Route | Complete
4 | Costing | Complete
5 | Literature search - ARD | 1 week
1 | RM Procurement for Lab work | 4 weeks | bar: 1 to 4
2 | Analytical requirements - Columns / Reagents procurement | 3 weeks | bar: 1 to 3
3 | Feasibility | 5 weeks | bar: 5 to 10
| Stage-01 | 4 days
| Stage-02 | 4 days
| Stage-03 | 4 days
| Stage-04 | 4 days
| Stage-05 | 4 days
| Stage-06 | 4 days
4 | Preparation or Procurement of IM and API standards | 5 weeks | bar: 5 to 9
IMT-1 Preparation
IMT-2 Preparation
API Standards
IMT-1,IMT-2 & API Chraterisation Report
5 | Tentative analytical method development and report for IP, IM & API | 6 weeks | bar: 5 to 10
6 | Analytical support For Feasibility | 5 weeks | bar: 5 to 9
7 | Feasibility Report | 2 days | bar: 6 to 10
| Stage-01 | 2 days
| Stage-02 | 2 days
| Stage-03 | 2 days
| Stage-04 | 2 days
| Stage-05 | 2 days
| Stage-06 | 2 days
8 | Forced Degradation followed by Identification and Procurement of Impurities and Report | 6 weeks | bar: 14 to 19
9 | Optimization | 12 weeks
| Stage-01 | 12 Days
| Stage-02 | 12 Days
| Stage-03 | 12 Days
| Stage-04 | 12 Days
| Stage-05 | 12 Days
| Stage-06 | 12 Days
10 | Identification of Impurities | 6 weeks | bar: 14 to 19
11 | Synthesis & Procurement of Impurities | 6 weeks | bar: 14 to 19
12 | Analytical support | 6 weeks | bar: 14 to 19
13 | Analytical Method Development | 6 weeks | bar: 6 to 11
14 | Analytical Method Development Report | 2 Weeks | bar: 12 to 13
15 | Optimization Report | 2days | bar: 10 to 21
| Stage-01 | 2 days
| Stage-02 | 2 days
| Stage-03 | 2 days
| Stage-04 | 2 days
| Stage-05 | 2 days
| Stage-06 | 2 days
16 | RM LIST | Complete
16 | Vendor Qualification | 4 Weeks | bar: 19 to 22
17 | Process Safety Studies - Hazop Studies & Risk Assessment [MSDS] | 4 weeks | bar: 19 to 22
18 | Demonstration of Process to the Engineers | 6 weeks | bar: 14 to 19
| Stage-01 | 1 week
| Stage-02 | 1 week
| Stage-03 | 1 week
| Stage-04 | 1 week
| Stage-05 | 1 week
| Stage-06 | 1 week
19 | Tentative specifications of RM | 4 weeks | bar: 14 to 17
| Tentative STP RM | 4 weeks | bar: 14 to 17
| Tentative specifications of IP, IM & API | 10 Weeks | bar: 11 to 20
Stage-01 [IP & IM] | bar: 14 to 23
Stage-02 [IP & IM]
Stage-03 [IP & IM]
Stage-04 [IP & IM]
Stage-05 [IP & IM]
Stage-06 [IP & API]
Tentative STP's of IP, IM & API
Stage-01 [IP & IM]
Stage-02 [IP & IM]
Stage-03 [IP & IM]
Stage-04 [IP & IM]
Stage-05 [IP & IM]
Stage-06 [IP & API]
20 | Equipment cleaning procedure | 9 Weeks | bar: 12 to 20
| Stage-01 | 1 week
| Stage-02 | 1 week
| Stage-03 | 1 week
| Stage-04 | 1 week
| Stage-05 | 1 week
| Stage-06 | 1 week
21 | Equipment cleaning analytical method [Based on UV Method] | 9 Weeks | bar: 12 to 20
1 week
1 week
1 week
1 week
1 week
1 week
22 | Process Write-up | 2 days | bar: 11 to 20
| Stage-01 | 2 days
| Stage-02 | 2 days
| Stage-03 | 2 days
| Stage-04 | 2 days
| Stage-05 | 2 days
| Stage-06 | 2 days
23 | BPR preparation | 2 days | bar: 12 to 20
| Stage-01 | 2 days
| Stage-02 | 2 days
| Stage-03 | 2 days
| Stage-04 | 2 days
| Stage-05 | 2 days
| Stage-06 | 2 days
24 | Lab Validation | 6 weeks | bar: 13 to 22
| Stage-01 | 1 week
| Stage-02 | 1 week
| Stage-03 | 1 week
| Stage-04 | 1 week
| Stage-05 | 1 week
| Stage-06 | 1 week
25 | Analytical Support for Lab Validation | 6 weeks | bar: 13 to 22
| Analytical Method Validation & Report | 2 days
Analytical Method Transfer
26 | Preparation of PDR (as per format provided by DQA) | 2 days | bar: 14 to 23
| Stage-01 | 2 days
| Stage-02 | 2 days
| Stage-03 | 2 days
| Stage-04 | 2 days
| Stage-05 | 2 days
27 | PDR review and approval by DQA | 2 days | bar: 15 to 24
| Stage-01 | 2 days
| Stage-02 | 2 days
| Stage-03 | 2 days
| Stage-04 | 2 days
| Stage-05 | 2 days
36 | Identification of Equipment for Scale-up
37 | Technology Transfer report by Engineers
38 | RM Procurement for Pilot batch
39 | Execution of Pilot batch
40 | Report on Pilot batch
41 | RM Procurement for Trail batch
42 | Execution of Trail batch
43 | Report on Trail batch
44 | Process Validation
45 | Process Validation report
46 | Finalization of all specifications and STPs
47 | Stability Study
48 | DMF Filing

## RM List
S.No. | Name of the Raw material | CAS Number | Remarks
1 | 1-(((2R,3S)-2(2,4-Difluorophenyl)-3-methyloxiran-2-yl)-methyl)-1H-1,2,4-triazole | 127000-90-2
2 | 1.65 M lithium bis(trimethylsilyl)amide in THF | 4039-32-1
3 | Acetone cyanohydrin | 75-86-5
4 | Diethyl dithiophosphate | 52857-42-8
5 | 2-bromo-4'-cyanoacetophenone | 20099-89-2
6 | di tert butylchloromethyl phosphate | 229625-50-7
7 | L-Lysine | 56-87-1
8 | tert-Butyl acetate | 540-88-5
9 | Sodium hydride | 7646-69-7
10 | Iodine | 7553-56-2
11 | THF | 109-99-9
12 | Aqueous HCl | 7647-01-0
13 | IPA | 67-63-0
14 | Ethyl acetate | 141-78-6
15 | Sulfuric acid | 7664-93-9
16 | MTBE | 1634-04-4
17 | Ethanol | 64-17-5
18 | Triethylamine | 121-44-8
19 | Trifluoroacetic acid | 76-05-1
20 | Sodium hydroxide | 7646-69-7
21 | Activated Charcoal | 7440-44-0
22 | Sodium chloride | 7647-14-5
23 | Sodium thiosulfite | 7772-98-7